## Sheet1
部门 | 测试角色 | 补录业务 | OI | NS | 录入 | 导入 | 导入人员 | 补录进度 | 说明
销售部 | 销售部长和组长 | 采购订单 |  | 是 |  | 是 | Lucky |  | 审批通过的直接导入
|  | 预付款申请单 |  | 是 |  |  |  |  | 需要执行审批流程
|  | 头程业务 | 是 | 是 | 是 |  |  |  | 全部录入
|  | 商品分配 | 是 | [5 empty] | 批量或一键操作
|  | B2C发货 | 是 |  | 是
|  | B2C售后 | 是 |  | 是
|  | 调拨指令 | 是 |  | 是
|  | 采购建议 |  | 是 |  |  |  |  | 修改现有脚本
| 销售人员 | 商品刊登 | [6 empty] | 目前只需要刊登到EBAY平台
|  | B2C发货 | 是 |  | 是
|  | B2C售后 | 是 |  | 是
跟单组 | 跟单员 | 采购订单 |  | 是 |  | 是 | Lucky |  | 需要跟单员测试采购订单变更的业务场景
|  | 预付款申请单 |  | 是 | 是
|  | 报关文档打印 | [6 empty] | 需要修改打印逻辑
|  | 采购发票 |  | 是 |  | 是 | Lucky |  | Jason负责发票匹配脚本
|  | 采购异常通知 | 是
|  | 质检异常通知 | 是
|  | 采购退换货 | 是 | 是 | 是 |  |  |  | 同步的退货申请状态需要修改；
仓库 | 库管员 | 入库 | 是 | [5 empty] | 采购入库、销售退货、调拨入库
|  | 出库 | 是 | [5 empty] | 销售出库、采购退货、调拨出库
|  | 收费清单 | 是 | [5 empty] | 在备注字段中写明收费项
|  | 盘点 | 是 | 是 |  | 是
财务 | 出纳 | 收付款 |  | 是
|  | 现金银行报表 |  | 是
| 会计 | 审核发票 |  | 是
财务期初（11月30日）
|  | 日记账 |  | 是 |  | 是
|  | 费用报告 |  | 是 | 是 | 是 |  |  | 录入10张单据，其他导入。
|  | 出口退税 |  | 是 | 是
|  | 本地化财务报表 |  | 是
|  | 整理采购发票 |  | 是 | 是 | 是 | Lucky |  | 注意，此部分在正式环境进行；
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 标记黄色部分暂时不用补录，还在测试中。
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 不能选择批次